## UDG-1 Contracts
UDG-1
No | Region | MA | UDG | Description of Project | Investment Type | Lot No | Contractor | Description of Contract | Total Contract Amount (GH₵) | Approved Net Additional Cost (Top-up amount) | Revised Contract Amount (GH₵) | % Physical Works Completed | Status | Start Date | Original Duration (mths) | Expected Completion Date | Approved Time Extension (mths) | Revised Completion Date
1 | Northern | Sagnarigu | UDG -1 | Rehabilitation of Urban Road and Construction of Storm Water Drain at Ward K, Sagnarigu | Road | Lot 1 | Iddal Company Ltd, P. O. Box 9785, Accra | Construction of Road (0.7km) with 1.5km Roadside Drains, 1No Box Culvert, 1.2km Pedestrian Walkway and Installation of 19No Street Lighting Faciities at Ward K, Sagnerigu | 4481741 | 397063.43 | 4878804.43 |  | Completed | 2020-06-29 | 9 | 2021-03-29 18:00 | 8 | 2021-11-28 02:00
2 | Northern | Sagnarigu |  |  | Storm Water Drain | Lot 2 | DeGroup A. Limited, P. O. Box CT3609, Cantonments-Accra | Construction of 4.0 x 2.0m (0.3km) and 2.5m x 1.5m (0.5km) Storm Drains at Wark K, Sagnerigu | 4736806.73 | 691144 | 5427950.73 |  | Completed | 2020-06-29 | 9 | 2021-03-29 18:00 | 8 | 2021-11-28 02:00
3 | Savannah | East Gonja | UDG -1 | Redevelopment of Salaga Market | Market | N/A | Mawums Company Limited, P. O. Box CT 4222, Cantonments-Accra | PHASE 1: Construction of 1No 2-storey Double Bank 40-Unit Lockable Stores, 1No Meat Shop and 1No 18-Seater W.C. Toilet Facility and Paving Works (318 sq.m) at Salaga Market | 2375716.5713 | 0 | 2375716.5713 |  | Completed | 2020-06-30 | 9 | 2021-03-30 18:00 | 8 | 2021-11-29 02:00
4 | North East | East Mamprusi | UDG -1 | Construction of Transport Terminal at Nalerigu | Transport Terminal | N/A | Saitama Enterprise Limited, P. O. Box CT 958, Cantonments-Accra | PHASE 1: Construction of 1No 2-Storey Multi-purpose Block comprising of Passenger Waiting Area, Ticketing Rooms, Offices, Police Post, Fire Post, Washrooms and External Paving Works (2400 sq.m) at Nalerigu Transport Terminal | 3238464.6 | 0 | 3238464.6 | 65% | Ongoing | 2020-07-12 | 9 | 2021-04-11 18:00 | 16 | 2022-08-11 10:00
5 | Upper West | Wa | UDG -1 | Redevelopment of Fadama Market, Wa | Market | Lot 1 | Q & Q E C Limited, P. O. Box WY 1243, Kwabenya-Accra | Construction of 2-Storey 19No Lockable Stores, 1No Town Hall with Restaurant and Washroooms at Fadama Market, Wa | 2190411.35 | 0 | 2190411.35 |  | Completed | 2020-06-22 | 9 | 2021-03-22 18:00 | 11 | 2022-02-20 08:00
6 | Upper West | Wa |  |  | Market | Lot 2 | Licos Enterpriae Limited, P O. Box 623, Wa | Construction of 2-Storey 46No Lockable Stores, 1No Health Post, 1No Creche and Washrooms at Fadama Market, Wa | 2042949.17 | 0 | 2042949.17 |  | Completed | 2020-06-22 | 9 | 2021-03-22 18:00 | 2 | 2021-05-22 14:00
7 | Upper West | Wa |  |  | Market | Lot 3 | Satlink Limited, P. O. Box 189, Wa | Construction of 2-Storey 32No Lockable Stores, 1No Fire Post, 1No Police Post, Washrooms, Installation of 10No Security Lighting Facilities and External Paving Works (1612 sq.m) at Fadama Market, Wa | 2280807.86 | 0 | 2280807.86 |  | Completed | 2020-06-22 | 9 | 2021-03-22 18:00 | 2 | 2021-05-22 14:00
8 | Upper East | Bawku | UDG -1 | Rehabilitation of Urban Road at Bawku | Road | N/A | Myturn Co. Ltd. P.O. Box 146 Bolgatanga | Upgrading of GHA to Articulator Station Road (2.5km) with Walkways | 5462981.86 | 0 | 5462981.86 |  | Completed | 2021-05-02 | 9 | 2022-01-30 18:00 | 0 | 2022-01-30 18:00
9 | Upper East | Bolgatanga | UDG -1 | Construction of Mechnical Enclve for Automobile Artisans at Bolgatanga | Industrial Estate | Lot 1 | Bulba Ghana Limited P. O. Box 715, Bolgatanga | PHASE 1: Construction of 1.84m high concrete Retaining Wall (329m) and Earthworks (22,180 cu.m) | 2208635.94 | 0 | 2208635.94 |  | Completed | 2021-03-26 | 9 | 2021-12-24 18:00 | 0 | 2021-12-24 18:00
10 | Upper East | Bolgatanga |  |  | Industrial Estate | Lot 2 | Abdulahi A.S Limited P. O. Box 303, Tamale | PHASE 1: Construction of 2No 8-Unit Mechanical Workshop, 1No Police Post, Washrooms & External Works | 1999706.94 | 0 | 1999706.94 |  | Completed | 2021-03-26 | 9 | 2021-12-24 18:00 | 0 | 2021-12-24 18:00
11 | Bono East | Techiman | UDG -1 | Redevelopment of Nana Abena Market, Techiman | Market | Lot 1 | Alhaji &Madina Co. Ltd. P.O Box 1665 Adum- Kumasi | Construction of 2-Storey 89No Lockable Stores, 1No Creche, Washrooms and Instalation of 10No Security Lighting Facilities at Nana Abena Market | 3569148.55 | 0 | 3569148.55 |  | Completed | 2021-03-19 | 9 | 2021-12-17 18:00 | 6 | 2022-06-18 06:00
12 | Bono East | Techiman |  |  | Market | Lot 2 | Jaborah Constr. Ltd. P.O. Box SE 1085 Suame -Kumasi | Construction of 33No Lockable Stores, 1No Restaurant, Washroom and Installation of 6No Security Lighting Facilities at Nana Abena Market | 1976392.22 | 153884 | 2130276.22 |  | Completed | 2021-03-19 | 9 | 2021-12-17 18:00 | 6 | 2022-06-18 06:00
13 | Bono East | Techiman |  |  | Market | Lot 3 | Elim Twelve Seventy Ltd. P.O. Box 516 Techiman | Construction of 68No Market Stalls, Administration Block, INo Meat Shop, 1No Fire Post, 1No Police Post, 1No Health Post, Washroooms, Installation of 10No Security Lighting Facilities and Paving Works (1900 sq.m) at Nana Abena Market | 2010883.05 | 1227828.54 | 3238711.59 |  | Completed | 2021-03-19 | 9 | 2021-12-17 18:00 | 6 | 2022-06-18 06:00
14 | Bono | Sunyani | UDG -1 | Construction of Pedestrian Walkways and Installation of Street Lighting Facilities along the Principal Streets, Sunyani | Pedestrian Walkway | Lot 1 | Gyebeet Company Limited, P. O. Box T89, Old Tafo-Kumasi | Construction of Pedestrian Walkways (5km) on both sides of road from SSNIT Roudabout to Sunyani Technical University | 4347906.15 | 0 | 4347906.15 |  | Completed | 2020-07-17 | 9 | 2021-04-16 18:00 | 1 | 2021-05-17 04:00
15 | Bono | Sunyani |  |  | Street Light | Lot 2 | Prefos Limited, P. O. Box 1609, Kumasi | Supply and Installation of 233 Bouble-arm and 170 Single-Arm Street Lights with associated civil works and Rehablitation of 773 Single-Arm Street Lights with accessories | 4182883.5744 | 0 | 4182883.5744 |  | Completed | 2020-07-17 | 9 | 2021-04-16 18:00 | 0 | 2021-04-16 18:00
16 | Bono | Berekum East | UDG -1 | Redevelopment of Thursday Market, Berekum | Market | Lot 1 | Diamond Valley Construction Limited, P. O. Box 16, Berekum | Construction of 7No. 20-Unit Stalls, 1No. Police Post, 2No. Passenger Waiting Area, 1No. Toll Booth and Ticketing Room, Paving of Lorry Park (7,300sq,m), Supply and Installation of 30No. Galvanized Street Light Poles Fitted with LED Lamps | 2500259.93 | 0 | 2500259.93 |  | Completed | 2020-08-14 | 8 | 2021-04-14 08:00 | 0 | 2021-04-14 08:00
17 | Bono | Berekum East |  |  | Market | Lot 2 | Samotrust Company Limited, P. O. Box AN10370, Accra-North | Construction of 60No. Lockable Stores, 1No. Health Post, 1No. Fire Post, 1No. 10-Seater WC Toilet Facility with Bath/Urinal Platform, Supply of 2No. Containers | 2523565.42 | 0 | 2523565.42 |  | Completed | 2020-08-14 | 8 | 2021-04-14 08:00 | 0 | 2021-04-14 08:00
18 | Bono | Berekum East |  |  | Road | Lot 3 | Licos Enterprise, P. O. Box 623, Wa | Surfacing of Berekum East Thursday Market Roads (1.35km), Construction of Roadside Drains and Installation of Street Lighting Facilities | 2500049.24 | 0 | 2500049.24 |  | Completed | 2020-08-14 | 8 | 2021-04-14 08:00 | 13 | 2022-05-14 18:00
19 | Bono | Dormaa Central | UDG -1 | Construction of Transport Terminal, Dormaa Ahenkro | Transport Terminal | Lot 1 | Opatec Company Limited, P. O. Box 237, Techiman | Construction of Transport Terminal comprising of 2-Story1No 20Lockable Stores, Police Post, Fire Post, Washrooms, Installation of Security Lighting (7No Double Arm Lamps and 6No Single Arm Lamps) and Paving (5,268sq.m) at Dormaa Ahenkro | 3868621.61 | 1353655.94 | 5222277.55 |  | Completed | 2020-08-07 | 9 | 2021-05-07 18:00 | 13 | 2022-06-07 04:00
20 | Ashanti | Obuasi | UDG -1 | Rehabilitation of Selected Urban Roads, Obuasi | Road | Lot 1 | Justmo Construction Limited, P. O. Box MC 01041, Takoradi | Rehablitation of Mactina Junction - Government Hill - Nyamebekyerewith (2.6km) Walkways, Covered Concrete U-Drains at Obuasi | 6147590.09 | 0 | 6147590.09 |  | Completed | 2020-08-21 | 8 | 2021-04-21 08:00 | 13 | 2022-05-21 18:00
21 | Ashanti | Obuasi |  |  | Road | Lot 2 | Malsons Limited, P. O. Box 1647, Accra | Rehablitation of Mactina Junction - Government Hill - Nyamebekyerewith (2.4km) Walkways, Covered Concrete U-Drains at Obuasi | 6153658.46 | 624744.84 | 6778403.3 |  | Completed | 2020-08-21 | 8 | 2021-04-21 08:00 | 13 | 2022-05-21 18:00
22 | Ashanti | Asokwa | UDG -1 | Rehabilitation of Selected Urban Roads, Asokwa | Road | Lot 1 | Mmanab Company Limited, P. O. Box UP 561, KNUST-Kumasi | Rehabilitation of Agyaba Road (0.353km), Janet Amoakohene Road (0.242km), Presby Link (0.086km) and Amo Gottfried Road (0.514), Construction of storm water drains, walkways and Installaton of Street Lighting Facilities at Asokwa | 3617910.4 | 0 | 3617910.4 |  | Completed | 2020-07-22 | 6 | 2021-01-20 12:00 | 0 | 2021-01-20 12:00
23 | Ashanti | Asokwa |  |  | Road | Lot 2 | M. Gyebi Company Limited, P. O. Box 1394, Sunyani | Rehabilitation of Afanko Junction - Atonsu Bokoro Road (1.613km) and Access Road (0.1km), Construction of storm water drains, walkways and Installaton of Street Lighting Facilities at Asokwa | 5027116.6 | 705868.41 | 5732985.01 |  | Completed | 2020-07-22 | 6 | 2021-01-20 12:00 | 0 | 2021-01-20 12:00
24 | Ashanti | Asokwa |  |  | Road | Lot 3 | Seal and Tar Limited, P. O. Box 433, Accra | Rehabilitation of Atonsu S-Line (0.70km) and Milano Roads (0.65km), Construction of storm water drains, walkways and Installaton of Street Lighting Facilities at Asokwa | 3445214.05 | 0 | 3445214.05 |  | Completed | 2020-07-22 | 6 | 2021-01-20 12:00 | 0 | 2021-01-20 12:00
25 | Ashanti | Suame | UDG -1 | Constrcution of Storm Water Drains at Selected Locations, Suame | Storm Water Drain | Lot 1 | Dankus Dee Company Ltd, P. O. Box KS 4980, Kumasi | Construction of 2.0m x 1.5m Reinforced Concrete Storm Drain (0.23km), 1.5 x 1.5m Reinforced Contract Storm Drain (0.26km) and 4No Concrete Foot Bridge with Guard Rails and Horticulture Works at Anomangye Highways | 2547347.04 | 212206.86 | 2759553.9 |  | Completed | 2020-08-21 | 6 | 2021-02-19 12:00 | 5 | 2021-07-21 14:00
26 | Ashanti | Suame |  |  | Storm Water Drain | Lot 2 | Cephil Company Limited, P. O. Box EJ 439, Ejisu | Construction of 2.0m x 1.5m Reinfoced Concrete Rectangular Storm Drain (0.22km), 1.5 Diameter Pipe Drain (0.27km) with 2No. Concrete Footbridges Fitted with Guard Rails, Access Ramps and Steps at Maakro Market | 2566831.05 | 0 | 2566831.05 |  | Completed | 2020-08-21 | 6 | 2021-02-19 12:00 | 4 | 2021-06-21 04:00
27 | Ashanti | Suame |  |  | Storm Water Drain | Lot 3 | Living Grace Company Limited, P. O. Box 6948, Kumasi | Constrution of 2.0m x 1.2m Reinforced Conrete Storm Drain (0.34km), and 2.5m x 1.2m Reinforced Concrete Storm Drain (0.15km), 2No Box Culvert (2.0mx 1.2m), 10m long each) and 150m of 0.6m Concrete U-Drain at Kronum-Abuohia (Adonk Street) | 2615442.12 | 0 | 2615442.12 |  | Completed | 2020-08-21 | 6 | 2021-02-19 12:00 | 15 | 2022-05-21 18:00
28 | Ashanti | Suame |  |  | Storm Water Drain | Lot 4 | Alhaji & Madina Company Limited, P. O. Box 1665, Adum-Kumasi | Construction of 3m x 1.5m Reinforced Concrete Storm Drain (0.36km), Pipe Culvert, 2No Concrete Foot Bridge with Guard Rails and Horticulture Works at Tarkwa (Islamic School) | 3518308.5 | 312604.72 | 3830913.22 |  | Completed | 2020-08-21 | 6 | 2021-02-19 12:00 | 0 | 2021-02-19 12:00
29 | Ashanti | Suame |  |  | Storm Water Drain | Lot 5 | M/S Makossy Enterprise, P. O. Box 2266, Suame - Kumasi | Construction of 0.9m x 0.9m Concrete U-Drain (0.1km); 2.0m x 1.5m Storm Drain (0.17km), 1.8m Dia. Concrete Pipe Culvert (48m) and Double 0.9mm Dia. Pipe Culvert (120m) at Old Suame Market | 2546735.53 | 0 | 2546735.53 |  | Completed | 2020-08-21 | 6 | 2021-02-19 12:00 | 15 | 2022-05-21 18:00
30 | Ashanti | Old Tafo | UDG -1 | Rehabilitationn of Selected Urban Roads, Old Tafo | Road | Lot 1 | Messrs Gold Print & Constructions Services P. O. Box Ah 8716, Ahinsan - Kumasi. | Rehabilitation of Okess – Kwasi Oppong road (2.2km), Construction of storm water drains, culverts and walkway | 6398183.51 | 0 | 6398183.51 |  | Completed | 2020-08-17 | 9 | 2021-05-17 18:00 | 12 | 2022-05-17 18:00
31 | Ashanti | Old Tafo |  |  | Road | Lot 2 | Joevide Company Limited, P. O. Box 10205, Kumasi. | Rehabilitation of Akrugu, Pia, Dabanka and Sir John roads (2km), Construction of storm water drains and walkway | 6000696.32 | 0 | 6000696.32 |  | Completed | 2020-09-28 | 9 | 2021-06-28 18:00 | 12 | 2022-06-28 18:00
32 | Western North | Sefwi Wiawso | UDG -1 | Redevelopment of Sefwi Dwenae Market, Sefwi Wiawso | Market | Lot 1 | Wass Ghana Limited, P. O. Box CT 2764, Cantonments-Accra | Construction of 2-Storey 20No Lockable Stores, 80No Market Stalls, and Earthworks at Sefwi Dwenase Market | 2649934.74 | 0 | 2649934.74 |  | Completed | 2020-10-02 | 8 | 2021-06-02 08:00 | 6 | 2021-12-01 20:00
33 | Western North | Sefwi Wiawso |  |  | Storm Water Drain | Lot 2 | Jesseth Construction and Trading Limited, P. O Box KS 1048, Kumasi | Construction of 1.5m x 1.2m Reinforced Concrete Storm Water Drain (0.404km) and 0.6m U-Drains (0.35km) at Sefwi Dwenase Market | 2021789.7 | 0 | 2021789.7 |  | Completed | 2020-10-02 | 8 | 2021-06-02 08:00 | 6 | 2021-12-01 20:00
34 | Western | Effia - Kwesimitsim | UDG -1 | Rehabilitation of Selected Urban Roads and Construction of Storm Water Drainage Structures (Culverts, Roadside Drains), Effia-Kwesimintsim | Road | Lot 1 | M/S Kingspok Company Limited, P. O. Box 982, Takoradi. | Rehabilitation of Wamco - Cocoa Villa Road (1.4km), 1No 3m x 2m Double Box Culvert (12m Long) with Storm Water Drains and Filling of Culvert Approaches | 5707993.81 | 0 | 5707993.81 |  | Completed | 2020-08-05 | 9 | 2021-05-05 18:00 | 0 | 2021-05-05 18:00
35 | Western | Effia - Kwesimitsim |  |  | Storm Water Drain | Lot 2 | M/S Finishers Company Limited, P. O. Box MC 1920, Anaji - Takoradi, W/R | Construction of 6m x 1.5m Reinforced Concrete Storm Drain (0.62km) from Kojo Kumi Avenue, Kwesimintsim Total Filling Station and Kwesimintsim Hospital | 3297752.28 | 603050.51 | 3900802.79 |  | Completed | 2020-08-05 | 6 | 2021-02-03 12:00 | 0 | 2021-02-03 12:00
36 | Western | Effia - Kwesimitsim |  |  | Storm Water Drain | Lot 3 | M/S Mamanjia Limited, P. O. Box Ds 1647, Dansoman - Accra. | Construction of Culverts with Roadside Drains and Culvert Approach Fillings at White Diamonds, Anaji Choice Mall, Takoradi Technical Institute and I Adu Road | 4000270.26 | 0 | 4000270.26 |  | Completed | 2020-08-05 | 6 | 2021-02-03 12:00 | 7 | 2021-09-04 10:00
37 | Western | Effia - Kwesimitsim |  |  | Road | Lot 4 | M/S Opo-Max Enterprise Limited, P. O. Box Ks 13382, Kumasi - A/R. | Construction of Culverts with Roadside Drains and Filling of Culvert Approaches and Roadside Drains at Unicon Hostel Road, Mex Media Road (0.187km), Bulley Road (Apollo), CDH Road (Whindo) and Mpatado-Assakae Road | 3597351.95 | 0 | 3597351.95 |  | Completed | 2020-08-05 | 6 | 2021-02-03 12:00 | 0 | 2021-02-03 12:00
38 | Central | Mfantseman | UDG -1 | Construction of Transport Terminal at Mankessim | Transport Terminal | Lot 1 | Abbansco Concrete Product Limited, P. O. Box 153, Mallam-Accra | Construction of 2-Storey Administration Block with Offices and 9No Lockable Stores, 6No Passenger Waiting/Boarding Sheds and External Paving Works (13,884 sq.m) at Mankessim Transport Terminal | 4463034.52 | 290314.97 | 4753349.49 |  | Completed | 2020-06-05 | 12 | 2021-06-05 | 4 | 2021-10-29 06:00
39 | Central | Mfantseman |  |  | Transport Terminal | Lot 2 | Hal-Siita Enterprise, P. O. Box, Airport Accra | Construction of 0.22km paved access Road with Walkway, 1No Box Culvert, 241m Concrete Retaining Wall, 2No Toll Booths, Washrooms, Installation of 25No Security Lighting Facilities and reshaping of storm water Drainage Channel at Mankessim Transport Terminal | 3123099.15 | 478668.88 | 3601768.03 |  | Completed | 2020-06-05 | 12 | 2021-06-05 | 16 | 2022-10-05 06:00
40 | Central | Agona West | UDG -1 | Rehabilitation of Selected Urban Roads at Agona Swedru | Road | Lot 1 | Jacmenant Limited, P. O. Box CT902, Cantonments-Accra | Bituminous Surfacing of Esukonsten Street (0.7km), Construction of 0.56km Roadside Drain with 1No Culvert and Paving of Agona Swedru Town Hall Forecourt (1327 sq.m) | 2399473.25 | 394839.5 | 2794312.75 |  | Completed | 2020-06-06 | 12 | 2021-06-06 | 3 | 2021-09-06 06:00
41 | Central | Agona West |  |  | Road | Lot 2 | Kasmo Company Limited, P. O. Box 607, Koforidua | Bituminous Surfacing of Otabilkrom Link (0.40km) and Egya Ebusua Street (0.65km), Construction of 0.97km Roadside Drains with 1No Culvert | 2430480.83 | 0 | 2430480.83 |  | Completed | 2020-06-06 | 12 | 2021-06-06 | 3 | 2021-09-06 06:00
42 | Central | Agona West |  |  | Road | Lot 3 | Bea-Newt Company Limited, P. O. Box TN883, Teshie-Nungua-Accra | Bituminous Surfacing of Mahodwe Link (0.13km), Oheneba Duodo Street (0.15km), Nana K. Donkor Street (0.15km), Osama Street (0.25km), Construction of 0.7km Roadside Drains and Paving of Agona Swedru Taxi Station (1575 sq.msqm) and reshaping of storm water Drainage Channel | 2614287.61 | 0 | 2614287.61 |  | Completed | 2020-06-06 | 12 | 2021-06-06 | 3 | 2021-09-06 06:00
43 | Central | Awutu Senya East | UDG -1 | Redevelopment of Kasoa New Market | Market | Lot 1 | Prefos Limited, P. O. Box 4679, Cantonments-Accra | Supply and Installation of 160No Streetlight with 2No (50KV and 33KV) Transformers at Awutu Senya East | 1740711 | 0 | 1740711 |  | Completed | 2020-08-12 | 6 | 2021-02-10 12:00 | 0 | 2021-02-10 12:00
44 | Central | Awutu Senya East |  |  | Market | Lot 2 | Mamanjia Limited, P. O. Box 1647, Dansoman-Accra | Construction of 840m Reinforced Concrete Retaining Fence Wall and Pedestrian Railing (2.81km) at Kasoa New Market | 2795810.15 | 0 | 2795810.15 |  | Completed | 2020-08-12 | 9 | 2021-05-12 18:00 | 17.8 | 2022-09-05
45 | Central | Awutu Senya East |  |  | Market | Lot 3 | AS-Afrimp Ghana Limited, P. O. Box KN 4349, Kaneshie-Accra | Concrete Paving (8740sq.m) of Kasoa New Market | 2785255.1 | 0 | 2785255.1 |  | Completed | 2020-08-12 | 9 | 2021-05-12 18:00 | 0 | 2021-05-12 18:00
46 | Central | Awutu Senya East |  |  | Storm Water Drain | Lot 4 | Sabert Investments Limited, P. O. Box 3749, Accra | Construction of 1.2m Concrete U-Drain and 0.6m Concrete U-Drain (475m) and Channelization of Okudu River (0.335km) at Kasoa | 1540469.21 | 0 | 1540469.21 |  | Completed | 2020-08-12 | 9 | 2021-05-12 18:00 | 0 | 2021-05-12 18:00
47 | Volta | Hohoe | UDG -1 | Redevelopment of Hohoe Central Market | Market | Lot 1 | John Mork Construction & Trading Limited, P. O. Box 390, Hohoe | Construction of 2-Storey 62 Units Stores (Block A) at Hohoe Central Market | 3662138.55 | 320000 | 3982138.55 | 90% | Ongoing | 2020-08-10 | 9 | 2021-05-10 18:00 | 13.7 | 2022-06-29 19:00
48 | Volta | Hohoe |  |  | Market | Lot 2 | Crown of Victory Company Limited P.O.Box HP 668, Ho | Construction of 2-Storey 44-Unit Market Stores (Block B) at Hohoe Central Market | 1893191.34 | 210000 | 2103191.34 |  | Completed | 2020-08-10 | 9 | 2021-05-10 18:00 | 16.7 | 2022-09-05 19:00
49 | Volta | Hohoe |  |  | Market | Lot 3 | J.A Biney & Co. Limited, P. O. Box 1339, Dansoman-Accra | Construction of 144No Market Stalls, Ware House (Ground Floor), Creche, Police and Fire Post at Hohoe Central Market | 2323248.41 | 0 | 2323248.41 |  | Completed | 2020-08-10 | 9 | 2021-05-10 18:00 | 13.7 | 2022-06-29 19:00
50 | Volta | Ho | UDG -1 | Redeveopment of Ho Market | Market | Lot 1 | Omega A. Company Limited, P. O. Box AN 5099, Accra-North | Construction of 2- Storey 58-Units Shops, 24-Units Washroom, Restaurant and Other Ancillary Facilities | 3737782.53 | 959273 | 4697055.53 |  | Completed | 2020-09-11 | 10 | 2021-07-12 04:00 | 12 | 2022-07-14 20:00
51 | Volta | Ho |  |  | Market | Lot 2 | Silver Cross Estate Developers Compant Limited, P. O. Box CT 702, Cantonments-Accra | Construction of 2- Storey 84-Units Shops, 12-Units Washroom, Restaurant and other Facilities | 5729401.4 | 345229 | 6074630.4 |  | Completed | 2020-09-11 | 10 | 2021-07-12 04:00 | 12 | 2022-07-14 10:00
52 | Eastern | New Juaben South | UDG -1 | Nsukawo Basin Drainage Improvement Works at Koforidua | Road | Lot 1 | Obmike's Construction & Suppliers Limited, P. O. Box KF 584, Koforidua | Bituminous Surfacing of Seleted Road (0.254km), Construction of 2.5m x 2.5m Box Culvert and 1.2m Diameter Pipe Culvert (60m) at Ada | 1088476.32 | 0 | 1088476.32 |  | Completed | 2020-09-16 | 6 | 2021-03-17 12:00 | 6 | 2021-09-16
53 | Eastern | New Juaben South |  |  | Storm Water Drain | Lot 2 | Yusif Abdul Aziz Company Limited, P. O. Box STC 433, Accra | Channelization by Excavation of Nsukwao River Channel (0.407km), Construction of Retention Pond, Reinforced Concrete Chamber and Laying of Pipes near Victory Presby Church at Ada | 2395390.65 | 0 | 2395390.65 |  | Completed | 2020-09-16 | 6 | 2021-03-17 12:00 | 2.5 | 2021-06-01 13:00
54 | Eastern | New Juaben South |  |  | Storm Water Drain | Lot 3 | Per Springs Construction Company Limited, P. O. Box KF 584, Koforidua | Channelization by Excavation of Nsukwao River Channel between Ada Magazine and Cendimental (Nsukwao River - 0.866km and Tributory - 0.508km), Stone Lining of Selected Sections (0.238km) and Construction of 1No. 2.5m x 1m and 3m x 1m Box Culverts | 2508581.55 | 0 | 2508581.55 |  | Completed | 2020-09-16 | 6 | 2021-03-17 12:00 | 2.5 | 2021-06-01 13:00
55 | Eastern | New Juaben South |  |  | Storm Water Drain | Lot 4 | Montjoira Construction (Ghana) Limited, P. O. Box 16134, KIA - Accra | Channelization by Excavation of Nsukwao River Channel (2.141km) and Stone Lining of Selected Sections (0.479km) at Zongo Area | 2122032.5 | 0 | 2122032.5 |  | Completed | 2020-09-16 | 8 | 2021-05-17 08:00 | 3 | 2021-08-19 14:00
56 | Eastern | New Juaben South |  |  | Storm Water Drain | Lot 5 | Tabarikalla Company Limited, P. O. Box GP 19243, Accra | Channelization by Excavation of Nsukawo River, Construction of Pond, Laying of Pipes and Stone Lining (0.24km) of Selected Sections at Zongo Area | 2376665.77 | 0 | 2376665.77 |  | Completed | 2020-09-16 | 6 | 2021-03-17 12:00 | 6.5 | 2021-09-30
57 | Eastern | New Juaben South |  |  | Storm Water Drain | Lot 6 | Malsons Limited, P. O. Box 1647, Accra | Channelization by Excavation of Nsukwao River Cahnnel within SDA (Tributory - 0.524km) and YMCA Area (0.462km) and Stone Lining of Selected Sections (0.227km) | 1899648.61 | 0 | 1899648.61 |  | Completed | 2020-09-16 | 6 | 2021-03-17 12:00 | 3 | 2021-06-16 18:00
58 | Eastern | New Juaben South |  |  | Storm Water Drain | Lot 7 | Bea-Newt Company Limited, P. O. Box TN883, Teshie-Nungua-Accra | Construction of 2No. In-Line Storage (Ponds) and 2No. Weir on Nsukwao River Channel within SDA Area | 3273976.13 | 0 | 3273976.13 |  | Completed | 2020-09-16 | 8 | 2021-05-17 08:00 | 2 | 2021-07-17 04:00
59 | Eastern | Lower Manya Krobo | UDG -1 | Redevelopment of Agormanya Market | Market | Lot 1 | Hawkrad Construction Limited, P. O. Box 9244, Airport-Accra | Construction of 2-Storey 82No Lockable Stores at Agormanya Market | 2994643.92 | 1592667.5825 | 4587311.5025 | 85% | Ongoing | 2020-08-10 | 6 | 2021-02-08 12:00 | 18.5 | 2022-08-31
60 | Eastern | Lower Manya Krobo |  |  | Market | Lot 2 | Win-Meg Ventures Limited, P. O. Box 782, Ho | Construction of 2-Storey 106No. Lockable Stores at Agormanya Market | 3188180.06 | 4393893.58 | 7582073.64 | 80% | Ongoing | 2020-08-10 | 6 | 2021-02-08 12:00 | 20.5 | 2022-10-01
61 | Eastern | Birim Central | UDG -1 | Redevelopment of Nkwantanum Market | Market | Lot 1 | Kingspok Construction Limited, P. O. Box 982, Takoradi | Construction of 34 Lockable Stores and Passenger Waiting Area comprising: Conference Room, Restaurant, Offices) at Nkwantanum Market, Oda | 2553376 | 0 | 2553376 |  | Completed | 2020-10-08 | 10 | 2021-08-08 04:00 | 14 | 2022-10-08
62 | Eastern | Birim Central |  |  | Market | Lot 2 | Licos Enterprise Limited, P. O. Box 623, Wa | Construction of 34 Lockable Stores, Paving, Concrete U-drain and Refuse Container Base at Nkwantanum Market, Oda | 2931260.47 | 0 | 2931260.47 |  | Completed | 2020-10-08 | 10 | 2021-08-08 04:00 | 14 | 2022-10-08
63 | Eastern | Birim Central |  |  | Market | Lot 3 | Synbeck Gh, Limited, P. O. Box CT 1297, Cantonments, Accra. | Construction of 34 Lockable Stores, Creche, Fire Post, Health Post and Washroom at Nkwantanum Market, Oda | 2961660.6 | 0 | 2961660.6 |  | Completed | 2020-10-08 | 10 | 2021-08-08 04:00 | 14 | 2022-10-08
64 | Eastern | Abuakwa South | UDG -1 | Constrution of Urban Park at Kibi | Road | Lot 1 | Knapo Construction Ltd P.O. Box KS 9443 Adum-Kumasi | Construction of Access Road (0.5km) and Internal Infrastructure Facilities (Paving, Drains etc) at Urban Park at Kibi | 2045241.44 | 0 | 2045241.44 | 49% | Ongoing | 2021-06-21 | 6 | 2021-12-20 12:00 | 10 | 2022-10-20 16:00
65 | Eastern | Abuakwa South |  |  | Urban Park | Lot 2 | Jaborah Construction Limited, P. O. Box SE 1085, Suame-Kumasi | Construction of 3-Storey 44 Rooms Hostel at Urban Park at Kibi | 3863814.79 | 856588.58 | 4720403.37 | 93% | Ongoing | 2020-12-08 | 9 | 2021-09-07 18:00 | 14 | 2022-11-07
66 | Eastern | Abuakwa South |  |  | Urban Park | Lot 3 | Cephil Company Limited, P. O. Box 439, Ejisu | Construction of 300 seating capacity auditorium, restaurant and swimming pool at Urban Park at Kibi | 2729823.8 | 493784.29 | 3223608.09 |  | Completed | 2020-12-08 | 9 | 2021-09-07 18:00 | 14 | 2022-11-07 18:00
Formulas:
Expected Completion Date = [Start Date]+(([Original Duration (mths)]/12)*365)
Revised Completion Date = ([Start Date]+(([Original Duration (mths)]+[Approved Time Extension (mths)])/12)*365)
Revised Completion Date = [Expected Completion Date]+(([Approved Time Extension (mths)]/12)*365)

## UDG-2 Contracts
UDG-2
No | Region | MA | UDG | Description of Project | Investment Type | Description of Contract | Total Contract Amount (GH₵) | % Physical Works Completed | Status | Start Date | Original Duration (mths) | Expected Completion Date | Completion Date | Approved Time Extension (mths) | Completion Date
1 | Upper West | Wa | UDG-2 | Constrcution of Strom Water Drains at Wa | Storm Water Drain | Construction of 0.225km Reinforced Concrete Storm Drain (4.5m x 2.0m) and 0.250km Reinforced Concrete Storm Drain (4.5m x 1.6m) and 1No. 3-Cell 3mx3m Box Culvert at Wa | 3669372.21 | 55% | Terminated to be Re-awarded | 2021-05-18 | 9 | 2022-02-15
2 | Savannah | East Gonja | UDG-2 | Redevelopment of Salaga Market | Market | PHASE 2: Construction of 40 Units 2-Storey Lockable Stores at Salaga Market | 1559305.8 | 100% | Completed | 2021-04-14 | 9 | 2022-01-12
3 | Bono | Berekum East | UDG-2 | Rehabilitation of Roads | Road | Construction of British Inn Junction Road (0.289km), Construction of U-drain (596m) , Walkway and Installation of 8No Street Light | 2152915.55 | 100% | Completed | 2022-05-26 | 11 | 2023-04-25
| Bono | Berekum East |  | Redevelopment of Berekum Thursday Market | Market | Construction of 2-Storey 40-Units Lockable Store, Banking Hall, Offices and External Woks comprising: | 2422603.05 | 100% | Completed | 2022-05-26 | 11 | 2023-04-25
| Bono | Berekum East |  | Redevelopment of Berekum Thursday Market | Market | Construction of 2-Storey 48-Units Lockable Store with External Works comprising: | 2281385.93 | 100% | Completed | 2022-05-26 | 11 | 2023-04-25
| Bono | Sunyani | UDG-2 | Rehabilitation of Roads | Road | Construction of Social Welfare School to Nana Bosoma Market Road (1km) with 0.9mm Covered U-drain, Paved Walkway (1km) and Installation of 35No Street Light | 4083042.47 | 100% | Completed | 2022-04-16 | 11 | 2023-03-16
| Bono | Sunyani |  | Supply and installation of Street Light | Street Light | Supply and Installation of 380No Street Lights with associated civil works | 2900471.84 | 100% | Completed | 2022-11-07 | 6 | 2023-05-08
| Bono | Sunyani |  | Supply of 10No 12cu.m Metal Refuse Skip Containers and 1000No 240litres Plastic Refuse Containers | Refuse Collection | Supply of 10No 12cu.m Metal Refuse Skip Containers and 1000No 240litres Plastic Refuse Containers | 782080 | 100% | Completed | 2022-10-06 | 4 | 2023-02-04
| Bono | Sunyani |  | Supply of 1No Refuse Skip Loader Truck and 1No Refuse Compactor Truck | Refuse Collection | Supply of 1No Refuse Skip Loader Truck and 1No Refuse Compactor Truck | 1923740 | 100% | Completed | 2022-10-06 | 4 | 2023-02-04
| Bono | Dormaa Central | UDG - 2 | Rehabilitation of Transport Terminal, Dormaa Ahenkro | Transport Terminal | Rehabilitation of Old Transport Terminal: comprising Construction of 1No Passenger Waiting Shed, Construction of Fencewall (217m), paving (2584sq.m), Constructon of 6-Seater WC Toilet, Installation of 8 No Street Light and Drilling/Mechanization of 1No Borehole with Overhead Storage Tank | 2078187.97 | 100% | Completed | 2022-07-18 | 11 | 2023-06-17
4 | Bono East | Techiman | UDG-2 | Rehabilitation of Roads | Road | Upgrading of Agyeiwaa Road to DVLA Office (0.243km) and Link 1 Road (0.154km), Constrution of U-drains (0.59km) and Installation of 8No Streetlight | 2512918.42 | 100% | Completed | 2022-06-14 | 12 | 2023-06-14
| Bono East | Techiman |  | Rehabilitation of Roads | Road | Upgrading of Abanemu Roads (0.418km), Construction of 9mm U-drain (0.297km), 6mm U-drian (0.120) and 20 No. street light | 2902388.57 | 100% | Completed | 2022-06-14 | 12 | 2023-06-15
| Bono East | Techiman |  | Redevelopment of Market | Market | Nana Abena Market Road Junction Improvement Works (0.1km), Construction of Fencewall (2499 m2) and Construction of Interna Drainage System (0.9 km) | 2689533.71 | 100% | Completed | 2022-06-14 | 11 | 2023-05-14
5 | North East | East Mamprusi | UDG-2 | Construction of Transport Terminal | Transport Terminal | Construction of 2-Storey Commercial Building, Drain and Paving at Nalerigu | 2509934.91 | 65% | Ongoing | 2022-04-14 | 12 | 2023-04-14
6 | Upper East | Bolgatanga | UDG-2 | Construction of Light Industrial Estate for Auto Mechanics | Industrial Estate | Construction of 1No. 2-Storey 40 – Units Lockable Stores and Fire Post at Tindonsobligo – Kalebeo, Bolgatanga | 2677729.62 | 100% | Completed | 2022-06-07 | 12 | 2023-06-07
[5 empty] | Industrial Estate | Construction of 4No. Mechanic Sheds and External, Civil/Electrical Works at Tindonsobligo – Kalebeo, Bolgatanga. | 2676362.46 | 100% | Completed | 2022-06-07 | 12 | 2023-06-07
|  | Bawku | UDG-2 | Redevelopment of Market | Market | Construction of 1No 2-Storey 48-Unit Lockable Store with External Works | 2815353.55 | 55% | Ongoing | 2022-09-13 | 12 | 2023-09-13
7 | Northern | Sagnarigu | UDG-2 | Revelopment of Market | Market | Construction of 1No 2-Storey Commercial Building comprising: 1No Banking Hall; Offices; 24No Lockable Stores, and 6No 12-Units Market Stalls with External Works at Sagnarigu | 3110772.01 | 35% | Ongoing | 2023-04-21 | 12 | 2024-03-04
|  |  |  | Revelopment of Market | Market | Construction of 1No 2-Storey 10 Lockable Stores , 1No Health Post, 1No Crèche, 1No 2-Storey 24 Lockable Stores with 2No Butcher/Meat Shops, at Sagnarigu Market | 2890629.85 | 40% | Ongoing | 2022-04-21 | 12 | 2024-04-21
8 | Ashanti | Suame | UDG-2 | Redevelopment of Market | Market | Construction of 1No 2-Storey 48-Units Lockable Stores, 1No 2-Storey with 17-Units Lockable Stores, 1No Police Post and 1No Health Post a at Kropo Market-Suame | 3516712.09 | 100% | Completed | 2022-09-08 | 11 | 2023-08-08
| Ashanti |  |  | Redevelopment of Market | Market | Construction of 1No 2-Storey 8-Units Lockable Stores and 18-Units WC Toilets, 4No 10-Units Market Stalls, 1No 20-Units Market Stall and 1No 5-Units Market Stalls, Demolition and External Works at Kropo Market-Suame | 3407104.61 | 98% | Completed | 2022-09-08 | 11 | 2023-08-08
| Ashanti | Old Tafo | UDG-2 | Rehabilitation of Roads | Road | Upgrading of Arizona Road (269m), Abed Roundabout Road (114m) and Richard Appiah Road (446) | 3455474.28 | 100% | Completed | 2022-08-01 | 12 | 2023-08-01
| Ashanti |  |  | Construction of Storm Water Drains | Storm Water Drain | Construction of 3m x 1.5m Storm Drain (200m), 1.2m U-Drain (50m), 0.9m U-Drain (165m) and 0.6m U-Drain (50m) at Santan | 1988800.11 | 100% | Completed | 2022-08-01 | 7 | 2023-03-09
| Ashanti |  |  |  | Storm Water Drain | Construction of 3.5m x 1.5m Storm Drain (138m) at Santan in the Old Tafo Municipality | 2469372.18 | 100% | Completed | 2022-08-01 | 7 | 2022-03-10
| Ashanti | Asokwa | UDG - 2 | Rehabilitation of Selected Urban Roads, Asokwa | Road | Rehabilitation of Atonsu S–Line Junction to S–Line Station Road (1.3km), Construction of U-drains (334m) and Installation 40 No. of Street Lights | 3683818.72 | 100% | Completed | 2022-05-18 | 8 | 2023-06-16
| Ashanti |  |  |  | Road | Rehabilitation of Kyerapatre Old Town Road Phase One (1.0km), Constrution of U-drain (334m) and Installation of 40 No Street Lights | 5212616.84 | 100% | Completed | 2022-05-18 | 8 | 2023-01-16
| Ashanti | Obuasi | UDG-2 | Construction of Storm Water Drains | Storm Water Drain | Construction of Reinforced Concrete 3.5m x 2m changed to 5m X 2.5m Storm Drain (630m = 390m) at Mensahkrom/Kunka New Town | 3526084.68 | 100% | Completed | 2021-05-20 | 8 | 2024-03-13
| Ashanti |  |  |  | Storm Water Drain | Construction of Reinforced Concrete 3.5m X 2m Storm Drain (630m = 560m) and Construction of 1No 3-Cell 3m x 2m Box Culvert at Nyameso to Born Again Junction | 3794704.13 | 100% | Completed | 2021-05-20 | 8 | 2022-11-14 | 2022-01-20 | 10 | 2022-11-20 04:00
| Ashanti |  |  |  | Storm Water Drain | Construction of Reinforced Concrete 3m x 2m = 2.5m X 1.5m Storm Drain (270m = 400m) from Stadium Junc. to Abompe + Constrution of 5m drain (6.5m x 3m) to connect the Box Culvert | 2411909.64 | 100% | Completed | 2021-05-20 | 6 | 2022-03-15 | 2021-11-20 | 0 | 2021-11-20
9 | Western North | Sefwi Wiawso | UDG - 2 | Redevelopment of Sefwi Dwenae Market, Sefwi Wiawso | Market | Construction of Market 120-Units Market Stalls and Earthworks at Edwinase Market and Transport Terminal | 2220178.78 | 100% | Completed | 2022-07-19 | 11 | 2022-03-16 | 2023-06-18 14:00 | 0 | 2023-06-18 14:00
[5 empty] | Market | Construction of 20-Units Lockable Stores and 40 -Units Market Stalls at Edwinase Market and Transport Terminal | 2070193.54 | 100% | Completed | 2022-07-19 | 11 | 2023-06-17 | 2023-06-18 14:00 | 0 | 2023-06-18 14:00
10 | Eastern | Birim Central | UDG-2 | Redevelopment of Old Premier Market, Akim Oda | Market | Construction of 68 Lockable Stores, Offices for GPRTU and Eatery at Old Premier Market | 3829932.28 | 70% | Ongoing | 2021-05-21 | 9 | 2024-03-18 | 2022-02-18 18:00 | 9 | 2022-11-19 12:00
| Eastern |  |  |  | Market | Precast Blocks Paving of Old Premier Market (3,000 sq.m) and Construction of 600mm Diameter Concrete 'U' Drain (240m) | 1704375.9 | 55% | Ongoing | 2021-05-21 | 6 | 2024-03-19 | 2021-11-19 12:00 | 13 | 2022-12-19 22:00
| Eastern | New Juaben South | UDG-2 | Redevelopment of Jackson Park (Urban Park) at Koforidua | Urban Park | Precast Blocks Paving of 15,000m2 at Jackson Park with 1No. Volley Ball Court (170m2) and 1No Basketball Court (480m2) | 2624737.65 | 100% | Completed | 2021-07-27 | 8 | 2024-03-20 | 2022-03-28 | 9 | 2022-12-26 18:00
| Eastern |  |  |  | Urban Park | Construction of 1No. Public Stand with Stores, Electrical room and 1No. VIP stand | 3389054.39 | 85% | Ongoing | 2021-07-27 | 10 | 2024-03-20 | 2022-05-27 | 7 | 2022-12-25 22:00
| Eastern |  |  |  | Urban Park | Construction of 1No. Restaurant with Pub and TV Theatre, 20-Seater Washroom | 2720022.94 | 100% | Completed | 2021-07-27 | 8 | 2022-03-22 | 2022-03-28 | 9 | 2022-12-26 18:00
| Eastern |  |  | Supply and Installation of Sreet Lights | Street Light | Rehabilitation of street lights by replacing 500chokes,700No Sodium bulbs,300complete LED lamps 700 No inginate, 200pcs 16mm dia x 4 underground cable, 10No streetlight control panel to newly developed areas | 449957.5 | 100% | Completed | 2021-07-27 | 6 | 2022-07-28 | 2022-01-27 | 6 | 2022-07-28 12:00
| Eastern | Lower Manya Krobo | UDG-2 | Rehabilitation of Urban Road | Road | Bitumen Surfacing of Canna and Kpanyas Road (1.20km). | 2507035.35 | 100% | Completed | 2021-05-21 | 9 | 2022-03-24 | 2022-02-18 18:00 | 7 | 2022-09-19 16:00
| Eastern |  |  | Constrution of Business Advisory Centre and Conference Facility at Odumasi Krobo | Business Advisory Center | Construction of Business Advisory Centre with Conference Hall and Hostle Facility | 4101338.79 | 100% | Completed | 2021-05-21 | 10 | 2022-03-25 | 2022-03-21 04:00 | 8 | 2022-11-19 12:00
| Eastern | Abuakwa South | UDG-2 | Construction of Urban Commercial Centre | Market | Cnstruction of 22No Lockable Stores, 1No Staff Office, Kichen, Restaurant, Warehouse, Open Hall for Supermarket and 7-Units Washrooms | 5796297.93 | 17% | Ongoing | 2023-05-03 | 12 | 2022-03-26 | 2024-05-02 | 0 | 2024-05-02
| Eastern |  |  |  | Market | Constrcution of 2No Creche with Palygrounds, Kichen, Rection, 23No Lockable Stores and 8-Units Washrooms | 4114304.54 | 19% | Ongoing | 2023-05-03 | 12 | 2022-03-27 | 2024-05-02 | 0 | 2024-05-02
11 | Volta | Ho | UDG-2 | Redevelopment of Ho Market | Market | PHASE 2: Construction of a Proposed Two Storey 54-Unit Shops, 12-Unit W/C, Main Entrance and Other Ancillary Facilities for the Phase -3 of the Redeveloping of the Ho Market | 3620441.32 | 85% | Ongoing | 2021-07-21 | 10 | 2022-03-28 | 2022-05-21 | 3 | 2022-08-22
| Volta |  |  |  | Market | PHASE 2: Construction of a Proposed Two Storey 37-Unit Shops, 24-Unit W/C, Mosque, Revenue Post and Other Ancillary Facilities for the Phase -3 of the Redeveloping of the Ho Market | 4211000 | 100% | Completed | 2021-07-21 | 10 | 2022-03-29 | 2022-05-21 | 3 | 2022-08-22
| Volta |  |  |  | Market | Construction of Precast Concrete Blocks Paving of 3085 Metres Square at the Ho Central Market | 1147967.03 | 100% | Completed | 2022-09-12 | 6 | 2022-03-30 | 2023-03-13 | 0 | 2023-03-13
| Volta | Hohoe | UDG-2 | Construction of Light Industrial Estate for Auto Mechanics | Industrial Estate | Construction of 16No of 4-Unit Garages at the Light Industrial Park | 2424359.34 | 95% | Ongoing | 2022-04-08 | 10 | 2022-03-31 | 2023-02-08 | 0 | 2023-02-08
| Volta |  |  |  | Industrial Estate | Construction of 10No Lockable Stores, 20-Unit Sanitary Facility, 1No Fire Post, 1No Police Post at the Light Industrial Park | 2490514.51 | 52% | Ongoing | 2022-04-08 | 10 | 2022-04-01 | 2023-02-08 | 0 | 2023-02-08
| Volta |  |  | Construction of Road | Road | Construction of Access Road 1.4km and U-drain (…km) to the Light Industrial Park and Paving of Hohoe Central Market 3000sq.m | 1535365.93 | 100% | Completed | 2022-04-08 | 8 | 2022-04-02 | 2022-12-08 | 0 | 2022-12-08
12 | Central | Agona West | UDG-2 | Rehabilitation of Selected Urban Road at Agona Swedru | Road | Bitumen Surfacing of Greenland Street in the Agona West Municipal PH.I (Km 0.00 - 0.70) | 2644453.75 | 100% | Completed | 2021-06-10 | 8 | 2022-04-03 | 2022-02-10 | 10.5 | 2022-12-26 09:00
| Central |  |  |  | Road | Bitumen Surfacing of Greenland Street in the Agona West Municipal PH.II (KM 0.70 - 1.40) | 3115976.12 | 100% | Completed | 2021-06-10 | 8 | 2022-04-04 | 2022-02-10 | 10.5 | 2022-12-26 09:00
| Central |  |  |  | Road | Bitumen Surfacing of Falcon Street & Eduful Street in the Agona West Municipal (0.350km) | 1214797.97 | 100% | Completed | 2021-06-10 | 6 | 2022-04-05 | 2021-12-10 | 12.4 | 2022-12-22 04:00
| Central | Mfantseman | UDG-2 | Rehabilitation of Selected Urban Roads and Paving of Transport Terminal | Road | Bitumen Surfacing of Selected Streets (1km) at Yamoransa and Paving (450 sq. m) of Anomabo Lorry Park in the Mfantseman Municipal. | 2132010.48 | 100% | Completed | 2021-06-26 | 6 | 2022-04-06 | 2021-12-26 | 9 | 2022-09-25 18:00
| Central |  |  | Redevelopment of Anomabo Market | Market | Construction of 60 Lockable Stores at Anomabo in the Mfantseman Municipality | 4792088.84 | 40% | Ongoing | 2021-06-26 | 10 | 2022-04-07 | 2022-04-26 | 12 | 2023-04-26
| Central | Awutu Senya East | UDG-2 | Redevelopment of Kasoa New Market | Road | Bitumen Surfacing of HFC-Timber Market Road (0.878km) and Timber Market – Main New Market Road (0.351km) | 2344460.35 | 100% | Completed | 2021-07-03 | 8 | 2022-04-08 | 2022-03-03 08:00 | 7 | 2022-10-02 06:00
| Central |  |  |  | Market | PHASE 2: Precast Blocks Surfacing of Kasoa New Market (8,740sq.m) | 1998324.25 | 100% | Completed | 2021-07-03 | 6 | 2022-04-09 | 2022-01-01 12:00 | 0 | 2022-01-01 12:00
| Central |  |  |  | Street Light | PHASE 2: Supply and Installation of 164 No Streetlights and 2No 50kVA Transformers at Kasoa New Market | 1882366.97 | 100% | Completed | 2021-07-03 | 6 | 2022-04-10 | 2022-01-01 12:00 | 0 | 2022-01-01 12:00
13 | Western | Effia-Kwesimintsim | UDG-2 | Rehabilitation of Urban Road | Road | Asphalt Surfacing of Assakae - Whindo Road (2.0km) and Bitumen Surfacing of Whindo Health Centre Road (0.5km). | 6204956.56 | 96% | Completed | 2021-05-26 | 9 | 2022-04-11 | 2022-02-23 18:00 | 6 | 2022-08-25 06:00
| Western |  |  | Construction of Solid Waste Collection Points and Supply of Metal Skip Containers | Refuse Collection | Construction of 10No. Refuse Collection Points and Fabrication of 10No Metal Skip Containers | 1885695 | 100% | Completed | 2021-05-26 | 6 | 2022-04-12 | 2021-11-24 12:00 | 11 | 2022-10-25
[8 empty] | Completed | 43
[8 empty] | Ongoing | 13
[8 empty] | Terminated/ Reawarded | 1
[8 empty] | Total | 57
Formulas:
Completion Date = [Completion Date]+(([Approved Time Extension (mths)]/12)*365)
Completion Date = [Start Date]+(([Original Duration (mths)]/12)*365)

## UDG-3 Contracts
UDG-3
No | Region | MA | UDG | Description of Project | Investment Type | Lot No | Contractor | Description of Contract | Total Contract Amount (GH₵) | Total Awarded (GHS) | Approved Net Additional Cost (Top-up amount) | Revised Contract Amount (GH₵) | % Physical Works Completed | Status | Start Date | Original Duration (mths) | Planned Completion Date | Approved Time Extension (mths) | Revised Completion Date
1 | Upper West | Wa | UDG-3 | Construction of 0.6km Road with Bitumen Surfacing, Box Culvert, Drains Speed Ramps, Road Line Markings and Road Signs from Kambali Cental Mosque to Dobile link Road (Phase 1) | Road | Lot 1 |  | Construction of 0.6km Road with Bitumen Surfacing, Box Culvert, Drains Speed Ramps, Road Line Markings and Road Signs from Kambali Cental Mosque to Dobile link Road (Phase 1) | 8534818.53 | #REF!
|  |  |  | Construction of Wa-Charia Road with Bitumen Surfacing , Road Line Markings and Road Signs | Road | Lot 2 |  | Construction of Wa-Charia Road with Bitumen Surfacing , Road Line Markings and Road Signs | 10823672.36
2 | Savannah | West Gonja | UDG-3 | Construction of 600 meters 3mx2m rectangular shaped drain and 260m, 0.9x0.9m U drain from Ngbaripe to Al Manara | Storm Drain | Lot 1 |  | Construction of 600m 3m x 2m rectangular drain and 260m, 0.9m dia. U drain from Ngbaripe to Al Manara | 4651020 | #REF!
|  | East Gonja | UDG-3 | Transport Terminal with 6750m2, fencing wall with 2No security booths, busparking canopy and compound lighting | Transport Terminal | Lot 1 |  | Transport Terminal with 6750m2, fencing wall with 2No security booths, busparking canopy and compound lighting |  | 0
3 | Bono | Berekum East | UDG-3 | Construction of a 8No. 14 Unit open market stalls, 2No. Pavilions, Construction of a 2No. Sheds, 3No. Speed ramps, 1No. Fire Hydrant, 1No Solar operated traffic light and street lighting and Paving of access to Market | Market | Lot 1 |  | Construction of a 1No. 2-Storey 56 Unit Lockable store + 1No. Meat Shop + 100m U drain | 4057414.68 | #REF!
[5 empty] | Market | Lot 2 |  | Construction of 4No. 14 Unit Open Market Stalls, 2No. Pavilions and Paving of Market Access and Spaces | 2450700 | #REF!
[5 empty] | Market | Lot 3 |  | Construction of a 2No. Shed + Paving of market spaces + 3No. Speed ramps + 1No. Fire Hydrant + 1No Solar operated traffic light + street lighting | 2714271.23 | #REF!
|  | Sunyani | UDG-3 | Construction of Reinforced Concrete Storm Drain (500x3x3 depth meters), 400m of 0.9 U-Drain, and Levelling to Reclaim 3 acres Old Dump Site | Storm Drain | Lot 1 |  | Abetifi Storm Drain (600m)- Sunyani | 8980915.24 | #REF!
|  |  |  | Construction of 1.40Km Tarred Road with 1,400m 0.60m and 0.9m Slabbed U-Drains 3x3(M) Double Cell Culvert ,paved 1400m walkways and 47No.Single Arm Street Light, 47No. luminaries | Road | Lot 2 |  | Jubilee Park Link Road (1.40km) with U Drains and Culvert | 16554903.2 | #REF!
|  |  |  | Procure 1No. 20m High Altitude Street Light maintenance Vehicle | Street Light | Lot 3 |  | Supply of 1No. 14m High Altitude Operation Truck (GOODS) | 1750897.87 | #REF!
|  | Dormaa Central | UDG-3 | Construction of 1No. 2-Storey 56 Unit Lockable stores, 8No. 14 Unit Open Market stalls, Creche and Improvement of access to Market spaces including street lighting water , WC toilet | Market | Lot 1 |  | Lot 1 - Construction of 1No. 2-Storey 56 Unit Lockable stores, 8No. 14 Unit Open Market stalls, Creche and Improvement of access to Market spaces including street lighting | 5283699.15 | #REF!
4 | Bono East | Techiman | UDG-3 | Upgrade Saanse Road and Gyaase Loop and Link (850m) - consisting of 0.6m U-drain (1300m), 0.9m U-drain (400m), 1No. 0.9 diametre pipe culverts, 1.2m diameter culverts , road line markings (2550m), subbase, primer and 1st seal and 2nd seal, 50No. Streetlights 4No. speed humps | Road | Lot 1 |  | Upgrading of Saanse Road (322.22m) and Gyaase Loop and Link (456.43m), Total Length = 778.65m | 7252503.95 | #REF!
|  |  |  | Upgrade Millennium Park Road Phase 1 (3.km): (3500m): consisting of 0.6m U-drain, 3,500m, 0.9 diameter pipe -culvert (2No), 0.9m U-drain outfall (300m), roadworks (2000m), (sub-base, base, primer and 1st seal and 2nd seal), Layby (2No.) walkway works (4km), street lights 40No., speed humps-4No. | Road | Lot 2 |  | Upgrading of Millennium Park Roads (1.86km) | 12275912.18 | #REF!
|  |  |  | Bituminous Surfacing of Nana Awerempem Street (Koo Guy Road) - (1.08km) and Construct traffic signals at three major intersections in Techiman | Road | Lot 3 |  | Upgrading of Nana Awerempem Roads (847.28m) | 4994210.49 | #REF!
|  |  |  | Construction of Phase 1 of Multi-purpose urban park consisting of an athletic oval, fenced inner-perimeter, dressing room, and 6No. Security lights and construct 2No. social centres with two offices, snack bars, 6-seater water closet toilet, and water connection | Urban Park | Lot 4 |  | Urban Park and Social Centre | 4000479.9 | #REF!
|  | Nkoranza South | UDG-3 | Development of market (Phase 1) Construction of 2-storey, 50-unit comprising 47 lockable stores, 1No police post, 1No fire office, 1No health post; 50 unit stalls, 2-unit creche and 1no. office with 3-seater w/c toilet, drill and mechanize 2no. boreholes | Market | Lot 1 |  | 2-Storey 50-Unit Lockable Stores | 3645301.92 | #REF!
[5 empty] | Market | Lot 2 |  | Police Post, Health Post and 6-Seater WC | 1457961.93 | #REF!
[5 empty] | Market | Lot 3 |  | 100-Unit Stalls and 2-Unit Creche | 2692357.31 | #REF!
5 | North East | East Mamprusi | UDG-3 | Construction of 2-Storey 80Lockable Stores, 72 No. stalls Fire hydrant, 20-Seater WC toilet, Electricity to Site, Street Lighting, Meat shop, Access road (provide the length of the road) into the market and paving along it and Mechanised Borehole | Market | Lot 1 |  | Construction of 2-Storey 80 No. Lockable stores |  | 0
[5 empty] | Market | Lot 2 |  | Construction of 72No. Stalls, 20 Seater Toilet Facility and External works
6 | Upper East | Bolgatanga | UDG-3 | Construction of 1.2km road from Akutatingane Junction to Bolga ECOMOG junction through the Soe Doctors Bangalows with double seal bituminous sealing 0.6m U drain and provision of 40N0 metal street poles and 40N0 LED street lamps | Road | Lot 1 |  | Construction of 1.2km road from Akutatingane Junction to Bolga ECOMOG junction through the Soe Doctors Bangalows |  | #REF!
|  | Bawku | UDG-3 | Redevelopment of Bawku Central Market – Phase II: Construction of 2No. 2 storey 84No. Lockable Stores, 2-storey banking facility, walkways and paved area (2,000sq meter) | Market | Lot 1 |  | Construction of 44No Lockable stores and external works |  | #REF!
|  |  | UDG-3 |  | Market | Lot 2 |  | Construction of 40No Lockable Stores and 2-storey Banking facility |  | #REF!
|  |  | UDG-3 |  | Market | Lot 3 |  | Paving of existing Market square (2000sqm) |  | #REF!
7 | Northern | Sagnarigu | UDG-3 | Construct 20 Seater WC Toilet, Urinal with hand washing facility and external works 350m paved lorry park and within the market, drainage system and electrical works (including 40 security lights), Police and Fire Service post at Sagnarigu community market:, Phase II | Storm Drain | Lot 1 |  | Construction of 235m long 4.5m × 1.5m reinforced concrete storm drain at Kalpohini | 6661060.48 | #REF!
[5 empty] | Road | Lot 2 |  | Construction of 0.9Km road with Drains, road marking, street lights at Katariga off the Tamale-Kumbungu road | 14565885.21 | #REF!
[5 empty] | Market | Lot 3 |  | Construction of 2- storey 40No. Lockable stores, 2-storey 24No. Lockable stores, 2-storey banking facility and External works (Paving of Lorry/parks) at Jisonayili | 9544020.66 | #REF!
[5 empty] | Market | Lot 4 |  | Construction of 2-storey 22No. Locakable stores with a Police post, a Creche, Clinic, 72 No. Stalls and Rehabilitation of 2No existing washrooms at Jisonayili | 8631803.83 | #REF!
|  | Yendi | UDG-3 | Construction of 2 Storey 60No. Lockable Stores, External works (Paving of car park and lorry park) | Market | Lot 1 |  | Construction of 2 Storey 60no. Lockable Stores |  | #REF!
[5 empty] | Market | Lot 2 |  | External works (Paving of car park and lorry park) |  | #REF!
|  |  |  | Construction of 0.45km Asphaltic road on Kumfong link road with 300m, 0.9m diametre U-drain with 600m, 0.6m Diametre U-drain and 1No. 1.8mX1.5mX12m single cell box culvert. 15No. Street lights, 300m pedestral walkway with pavement blocks | Road | Lot 3 |  | Construction of 0.45 Kumfong link road |  | #REF!
8 | Ashanti | Suame | UDG-3 | Complete Kropo Market (Phase II) Construct 72 units lockable store, 0.25Km surface dressing with double seal, 500m U Drain (0.45m) U- Drain and pavement of Internal and External Area (2000m2), complete 20 No. streetlights at Kropo market. | Market | Lot 1 |  | Construction of Type 'E1' 40 Units, Store Type 'D1' 32 Units, External Works and 110m of Road with Drainage System at Kropo Market, Suame - Kumasi |  | 0
|  |  |  | Construction of 90 No locakable shops, first Aid and Fire station block, Lorry terminal, 20 seater WC, 20No complete streetlight, 500m2 pavement 1Km access road and external works at Old Suame market | Market | Lot 2 |  | Construction of 60No. Lockable Shops at Old Suame Market |  | 0
[5 empty] | Market | Lot 3 |  | Construction of 30No Lockable Shops at Old Suame Market |  | 0
[5 empty] | Solid Waste Mgt | Lot 4 |  | Procure 2No. Cesspool emptiers |  | 0
|  | Old Tafo | UDG-3 | Construction of 4 No. 250m long, 4x4 rectangular reinforced concrete storm drain, 8 No. concrete footbridges and landscaping/greenery | Storm Drain | Lot 1 |  | Construction of reinforced concrete Storm Drain at Pankrono |  | 0
[5 empty] | Storm Drain | Lot 2 |  | Construction of reinforced concrete Storm Drain at Tafo, Abed |  | 0
[5 empty] | Storm Drain | Lot 3 |  | Construction of reinforced concrete Storm Drain at Tafo Mosque |  | 0
[5 empty] | Storm Drain | Lot 4 |  | Construction of reinforced concrete Storm Drain at Tafo Ahenbrono |  | 0
|  | Asokwa | UDG-3 | Construction of 2 Storey 50-Unit Multi Purpose Market Store Complex with 100 Seater Capacity Conference Hall, 2No banking halls, 10No. Washroom, Recreational Centre and Paved Area (400m2) | Market | Lot 1 |  | Construction of Multi Purpose Market Complex | 9675676.19 | #REF!
|  |  |  | Upgrading of 0.75 Km Ahinsan Old Town to Ahinsan Estate Link with Double Seal Surface dressing, 2No.1.2 Diametre Pipe Culvert 2,320 m2 Ground Stabilization. 1,620m Concrete Open U-Drains, 2,800 m Road Markings and Crossings, 30No. Complete Street Lighting System and 7No. Road Signs | Road | Lot 2 |  | Construction of Old Ahinsan to Ahinsan Estate Road | 8824762.43 | #REF!
|  | Obuasi |  | Redevelopment of Obuasi Urban Park into a multi purpose modern recreational park (61,949.9 m2) with construction of 2-storey 800-seater capacity community/ entertainment Centre with offices and bar, fence with security booth and ticketing points | Urban Park | Lot 1 |  | Construction of 2-Storey 800 seater capacity Auditorium with Conference Rooms | 14388715.84 | #REF!
|  |  |  | Construction of 400m (5×2.5)m Reinforced Concrete Drains at Mensahkrom. | Storm Drain | Lot 2 |  | Construction of Concrete Drains | 1724084.85 | #REF!
|  | Kwabre East |  | Bituminous surfacing of: 2.5km Ahwiaa-Asona-Super Texas road with 0.9m U-side drains on both sides, 2.0m wide pedestrian walkway on both sides with 1No. 3 Cell Box culvert (3000m x 3000mm); 2.2km Anyinam Nana Appiah Area Road, with 0.6m U- side Drains on both sides, 1.5m pedestrian walkway on both sides with 3No. access culvert; 1.7 km Mamponteng OK Academy to Bampanase - Fawoade MyBet Junction by pass Road, with 0.6m U-side Drains on both sides, 1.5m pedestrian walkway on both sides, 2m box culvert with 4No. access culvert | Road |  |  | Bituminous surfacing of 1.4km Ahwiaa-Asona-Super Taxas road with U drains on both sides, 1.4km Anyinam Nana Appaih area road with U drains and 1.0km Mamponteng OK Academy Road with U drains | 37135076 | #REF!
|  |  |  | Construction of Ph.1 of 1 No. Market facility with 80 No. lockable stores, (I Storey); 1655m2sandcrete brick pavement; 15No. 20Unit Stalls; 10-seater WC with 5No. public bathrooms, 1No mechanized boreholes with 5,000-liter overhead tank; 1 No. Waste Transfer Pad. | Market |  |  | Construction of Ahwiaa Market (Phase 1) |  | #REF!
|  | Ahafo Ano North |  | Undertake street electrification project in Tepa Township | Street Light | Lot 1 |  | Extension of electricity to Beposo - Pentecost and Beposo Local (Behind SHS areas) |  | #REF!
[5 empty] | Street Light | Lot 2 |  | Extension of electricity to Addai Amankwa, Kwame Awuah and new Ahenbronum areas |  | #REF!
9 | Western North | Sefwi Wiawso | UDG-3 | Construction of Phase III of Modern Market Complex made up of : (i)Construction of 100-Unit market stalls (2.1 x2.1m), 1No. 20-Unit Lockable Stores (23x15m), Earthworks and pavement (ii) Construction of 1no. 20 Seater Water Closet Toilet with 10 Bathrooms & 4 Urinal with Mechanised Borehole with Earth Works (iii)Procurement of 4No. 15cm3 communal refuse containers and construction of 4No refuse bays with concrete staircase . (iv)Construction of police post | Market | Lot 1 |  | Construction of Two (2) Number 28 Unit lockable stores | 3700050.01 | #REF!
[5 empty] | Market | Lot 2 |  | Construction of 11No. 14 unit open market stalls | 2170771.9 | #REF!
[5 empty] | Market | Lot 3 |  | Construction of 1No. Police post, Paving of access to market and market spaces, covering of existing drains, 2No. Skip containers and Refuse bins, 1No. Mechanised borehole and water storage facility | 1898291.73 | #REF!
10 | Eastern | Birim Central | UDG-3 | Construction of 0.9m Concrete U Drain, Reinforced Concrete box Culvert, 1800mm Precast Concrete pipe, 20m Trapezoidal Riprap Channel around Old Premier Market | Storm Drain | Lot 1 |  | Construction of 0.9m Concrete U Drain, Reinforced Concrete box Culvert, 1800mm Precast Concrete pipe, 20m Trapezoidal Riprap Channel around Old Premier Market | 2563108.85 | #REF!
|  |  |  | Bituminous Surfacing of Nkwantanum Road with road signs and marking & Construction of Concrete U Drains along Nkwantanum road | Road | Lot 2 |  | Bituminous Surfacing of Nkwantanum Road with road signs and marking & Construction of Concrete U Drains along Nkwantanum road | 5588715.06 | #REF!
|  | New Juaben South | UDG-3 | Redevelopment of Jackson Park Phase II Construction of 3 No. Public Stand 22.5mx9.5m, 1 No. Ceremonial Stage 22.5mx9.5m, 1 No. Gymnasium and furnishing (4 treadmills, 10 dumbbell kits set ,6 spinning bike, 4 cross training pushups wheel, 2 multi – purpose trainer, 6 outdoor table tennis table, 4 incline weight bench, 2 soundbar, 150 No. chairs, 4 No. bench ,20msq gym mat) , 1 No. Swimming Pool 34.2m x 13.6m, and associated Furnishings, 555m Wrought Iron Fence Wall 570m x 1.5m, Landscaping at the Cenotaph 350m2, Paving of 13,000sqm2, ambulance bay, fire station and 2 No. 50 KVA Electric power plant (Generator) | Urban Park | Lot 1 |  | Construction of 1No. Public Stand and 1No. Ceremonial stand at the Koforidua Jackson Park | 4218173.75 | #REF!
[5 empty] | Urban Park | Lot 2 |  | Construction of 555m Fence Wall, Paving of 6800m2 and Landscaping at the Koforidua Jackson Park | 5087585.93 | #REF!
[5 empty] | Urban Park | Lot 3 |  | Construction of 1No. Gym and 1No. Health Post at the Koforidua Jackson Park |  | #REF!
|  |  |  | Rehabilitation of 0.5km x 7.5m Apostolic and Pentoawala road by placing 80N/m2 paving blocks and 400m concrete drainage works | Road | Lot 4 |  | Rehabilitation of 0.277km Apostolic and Pentoawala Roads | 1908906.25 | #REF!
[5 empty] | Road | Lot 5 |  | Bitumen Surfacing of 0.7km Galloway to St. Dominic Roads | 1843282.05 | #REF!
|  | Lower Manya Krobo | UDG-3 | Construction of Atua Junction - Adjikpo Road (0.8km) | Road | Lot 1 |  | Construction of Atua Junction - Adjikpo Road (0.8km) | 6029658.64 | #REF!
|  |  |  | Construction of SAS George street from Bank Junction to Kodjomam (1.8km), Atua-Adjikpo Yokunya Road (0.8km), footbridge at Ketse, 2 | Road | Lot 2 |  | Construction of SAS George street from Bank Junction to Kodjoman Road (1.8km), footbridge at Ketse | 8420389.67 | #REF!
|  |  |  | Construction of 40m Storm Drain (5m x 1.5m) & Box Culvert (4m x 2m) at Manaam | Storm Drain | Lot 3 |  | Construction of 40m long 5m x 1.5m Storm Drain & Box Culvert (4m x 2m) at Manaam | 2185322.26 | #REF!
|  | Abuakwa South | UDG-3 | Construction of modern community market centre | Market | Lot 1 |  | Construction of Modern Community Market Center with Ancillary Facilities at Kyebi (Phase 2) | 4114304.54 | #REF!
|  | West Akim | UDG-3 | Bituminous surfacing of of selected roads (2.325km) and installation of 50No single arm street lights and road marking | Road | Lot 1 |  | Bitumen Surfacing of selected Roads of 2.325km with Streetlights at Jamestown, Asamankese | 8247497.61 | #REF!
11 | Volta | Ho | UDG-3 | Construction of Bituminous Surfacing (Double Seal) with double side drains (0.6m) of selected roads in Ho Township : (1) Charcoal Road (0.4km); (2) Star SHS to Scrap Top (0.54km); (3)Barracks New Town to Dave Junction (2.8km); (4)Bi Sam to Zion Junction (0.14km) |  | Lot 1 |  | Construction of Charcoal Road (0.4km), Star SHS to Scrap Top (0.54km), Blisam to Zion Junction (0.14km) |  | #REF!
[6 empty] | Lot 2 |  | Construction of Barracks New Town Road (CH0+000-CH1+000) |  | #REF!
[6 empty] | Lot 3 |  | Construction of Barracks New Town Road (CH1+000-CH2+130) |  | #REF!
|  | Hohoe | UDG-3 | Construction of Ph.2 of 32-Unit Lockable Stores, 108-Unit Market Stalls, completion of 1 No. 16-Unit Warehouses and Construction of Fence Wall (290m) around the Hohoe Central Market | Market | Lot 1 |  | Construction of 32-Unit Lockable Stores at Hohoe Central Market | 4307095.2 | #REF!
[5 empty] | Market | Lot 2 |  | Construction of 108-Unit Market Stalls, Completion of 1 No. 16-Unit Warehouse and Construction of Fence Wall (290m) Around the Hohoe Central Market | 3809078 | #REF!
|  |  |  | Development of Phase 2 of light industrial area with Construction of 8No. Garages and Construction of 1No. Health and Fire Post | Light Industrial Area | Lot 3 |  | Construction of 8No. Garages, 1No. Health and Fire Post | 4395349.38 | #REF!
12 | Central | Agona West | UDG-3 | Construction of (Phase 1) of 3-storey 60 No lockable stores with fire post, security post, creche and pavement of the forecourt (50mx3m at both side)of the stores and connection to electricity and water at Mandela in Agona Swedru. | Market | Lot 1 |  | Construction of Three Storey 60No. Lockable Shops at Mandela Market - Phase 1 | 11488459.55 | #REF!
|  |  |  | Resealing of 0.55 km Otabil road with minor drainade repair ramblte sprips and road line markinf og 0.55km | Road | Lot 2 |  | Construction of Otabilkrom Road (0.575km) with Double Seal Bituminous surfacing and Construction of Side Drain Slab Cover | 2662357.8 | #REF!
|  | Mfantseman | UDG-3 | Construction of 2 storey 36No lockable stores, including external works involving site preparation and clearance, access road, construction of box culvert, U drain, electrical installation, external water supply and distribution | Market | Lot 1 |  | Lot 1: Construction of two (2) Storey Thirty-Six (36) Number Lockable Stores and External Construction Works at Mankessim | 6566428.2 | #REF!
[5 empty] | Market | Lot 2 |  | Lot 2: External Construction Works at Mankessim | 4641079.72 | #REF!
|  | Awutu Senya East | UDG-3 | Construction (Bitumen Surfacing) of 4km road with 7,200m 0.6m U-drains, 200m 0.9m U-drains, 4No. 0.9m diameter pipe culverts, 3No. 1.2m diameter pipe culverts, 4km length of sub-base and stabilized base and 4km length of primer seal, first seal and second seal, road line markings and 5No. speed humps with walkways on both sides and inner roads (Assembly office block premises and Odupong Kpehe SHS) | Road | Lot 1 |  | Lot 1 - Construction of Ofaakor - Jei River Road with Side Drains and Culvert (3.5km) Double Seal Bituminous Surfacing | 33954207.7 | #REF!
|  |  |  | Construction of 3x3 double cell box culvert and filling of approaches | Storm Drain | Lot 2 |  | Lot 2 - Construction of Proposed Triple 3.0M x 3.0m Box Culvert & approach roads at Akweley, Kasoa | 4406391 | #REF!
|  |  |  | Pre-cast block pavement of Kasoa Old Market (8,000 sq.m) | Market | Lot 3 |  | Lot 3 - Construction of 8500sqm External Pavement works with precast concrete paver Blocks for Kasoa old Market | 3347086 | #REF!
|  |  |  | Construction of 3x3 double cell box culvert and filling of approaches | Storm Drain | Lot 4 |  | Lot 4 - Construction of Single 3.0m x 2.5m Box Culvert with approach roads at Rock City, Kasoa | 699176.54 | #REF!
|  | Assin Fosu | UDG-3 | Paving of Assin Foso Main Lorry Station & Construction of 4 No Passenger Waiting Rooms and Installation of 12No Street Light, WC toilet and provision of water | Transport Terminal | Lot 1 |  | Paving of Assin Foso Main Lorry Station and Construction of 4No Passenger Waiting Room with Installation of 12No Street Lights | 5990686.7 | #REF!
13 | Western | Effia-Kwesimintsim | UDG-3 | Construction of 1No. 2-Storey 30- Lockable Stores with (5) offices, pavement of lorry/taxi park(3,550 meter square) with concrete kerbs for Kwesimintsim lorry park | Transport Terminal | Lot 1 |  | Construction of 2No Fifty-Seven (57) Unit Lockable Shops and 4No Offices at Kwesimintsim, Paving of Kwesimintsim Lorry Station in Effia Kwesimintsim | 10000165.1 | 0
|  |  |  | Surface Dressing of Effia Town Roads (2.0Km), Construction of 1No. 3m x 2m x 12m long double box culvert with culvert Approach filling works at SSNIT Down and Anaji SSNIT Flats Loop Road (0.70Km) |  | Lot 2 |  | Surface Dressing of Effia Town Roads (0.7km), Construction of 1No 3m X 2m 12m long double culvert approach filling works at SSNIT Down and Anaji SSNIT Flats Loop Road (0.70Km) | 5504895.24 | #REF!
|  |  |  | Construction of Storm Drain from Anaji Choice Mart – Asare Oppong School to I- Adu (1.3 kilometers long) | Road | Lot 3 |  | Construction of 850m 4.5m x 1.5m Storm Drain from Anaji Choice Mart to I. Adu in the Effia Kwesimintsim Municipality | 12345550.25 | #REF!
|  |  |  | Construction of 300 Meters Long Storm Drain with 1No. 3m x 2m x 12m long double box culvert with culvert Approach filling works from Bankyease -Kwesimintsim. | Storm Drain | Lot 4 |  | Construction of 3No 3m x 2.5m box culvert at Effia and 2No 3m x 2.5m box culvert at Bankyease and 150m long Storm Drain in Effia Kwesimintsim Municipality | 5400227.93 | #REF!
|  | Ahanta West | UDG-3 | Construction of 1.5km road (Agona Nkwanta to Quarters), Re-gravelling and Construction of side drains, Construction of Culverts | Road | Lot 1 |  | Construction of 1.50km length of the proposed road (Agona Nkwanta to Quarters) - regravelling and construction of 0.6m side concrete drains, construction of 2no. 1.2m dia. culverts, construction of 1no. 0.9m dia. culvert, extension of the existing 3m x 2m box culverts, construction of 1no. 3m x 2.5m and 3m x 2m new box culverts, Double Seal bituminous surfacing. | 9891592.1 | #REF!
|  |  |  | Construction of 0.6km road (main road to chief's palace), Re-gravelling and Construction of side drains, Construction of culverts | Road | Lot 2 |  | Construction of 0.6km length of proposed road (main road to chief’s palace) - re-gravelling and construction of 0.6m side drains, construction of 2no. 1.2m dia. culverts, construction of 1no. 0.9m dia. culvert, Double Seal bituminous surfacing. | 4552108.22 | #REF!
14 | Oti | Krachi East | UDG-3 | Re-development of Ph.1 of Dambai Market to include:Construction of 32-Unit Lockable Stores | Market | Lot 1 |  | Construction of 32-Unit Lockable Stores |  | #REF!
15 | Ahafo | Asunafo North | UDG-3 | Construction of 2No. 2-Storey 28 Unit Lockable stores including sick bay , 1No. 40 Unit Lockable Stores , Security post, 14-Unit Open Market Stalls, 2No. Skip Containers and Creche, Improvement of access to Market and Market spaces, Street Lighting, Borehole and ground level water storage facility | Market | Lot 1 |  | Construction of 1No. 2-Storey 28 Unit Lockable stores including sick bay & Construction of 1No. 40 Unit Lockable Stores |  | #REF!
[5 empty] | Market | Lot 2 |  | Construction of 1No. 2-Storey 28 Unit Lockable stores, Security post, 14-Unit Open Market Stalls, 2No. Skip Containers and Creche |  | #REF!
[5 empty] | Market | Lot 3 |  | Improvement of access to Market and Market spaces, Street Lighting, Borehole and ground level water storage facility |  | 0

## UDG-4 Contracts
UDG-4
No | Region | MA | UDG | Description of Project | Investment Type | Lot No | Contractor | Description of Contract | Total Contract Amount (GH₵) | Approved Net Additional Cost (Top-up amount) | Revised Contract Amount (GH₵) | % Physical Works Completed | Status | Start Date | Original Duration (mths) | Planned Completion Date | Approved Time Extension (mths) | Revised Completion Date
1 | Upper West | Wa | UDG-3
2 | Savannah | West Gonja | UDG-3
|  | East Gonja | UDG-3
3 | Bono | Berekum East | UDG-3
|  | Sunyani | UDG-3
|  | Dormaa Central | UDG-3
4 | Bono East | Techiman | UDG-3
|  | Nkoranza South | UDG-3
5 | North East | East Mamprusi | UDG-3
6 | Upper East | Bolgatanga | UDG-3
|  | Bawku | UDG-3
UDG-3
UDG-3
7 | Northern | Sagnarigu | UDG-3
|  | Yendi | UDG-3
8 | Ashanti | Suame | UDG-3
|  | Old Tafo | UDG-3
|  | Asokwa | UDG-3
Obuasi
Kwabre East
Ahafo Ano North
9 | Western North | Sefwi Wiawso | UDG-3
10 | Eastern | Birim Central | UDG-3
|  | New Juaben South | UDG-3
|  | Lower Manya Krobo | UDG-3
|  | Abuakwa South | UDG-3
|  | West Akim | UDG-3
11 | Volta | Ho | UDG-3
|  | Hohoe | UDG-3
12 | Central | Agona West | UDG-3
|  | Mfantseman | UDG-3
|  | Awutu Senya East | UDG-3
|  | Assin Fosu | UDG-3
13 | Western | Effia-Kwesimintsim | UDG-3
|  | Ahanta West | UDG-3
14 | Oti | Krachi East | UDG-3
15 | Ahafo | Asunafo North | UDG-3

## UDG-5 Contracts
UDG-5
No | Region | MA | UDG | Description of Project | Investment Type | Lot No | Contractor | Description of Contract | Total Contract Amount (GH₵) | Approved Net Additional Cost (Top-up amount) | Revised Contract Amount (GH₵) | % Physical Works Completed | Status | Start Date | Original Duration (mths) | Planned Completion Date | Approved Time Extension (mths) | Revised Completion Date
1 | Upper West | Wa | UDG-3
2 | Savannah | West Gonja | UDG-3
|  | East Gonja | UDG-3
3 | Bono | Berekum East | UDG-3
|  | Sunyani | UDG-3
|  | Dormaa Central | UDG-3
4 | Bono East | Techiman | UDG-3
|  | Nkoranza South | UDG-3
5 | North East | East Mamprusi | UDG-3
6 | Upper East | Bolgatanga | UDG-3
|  | Bawku | UDG-3
UDG-3
UDG-3
7 | Northern | Sagnarigu | UDG-3
|  | Yendi | UDG-3
8 | Ashanti | Suame | UDG-3
|  | Old Tafo | UDG-3
|  | Asokwa | UDG-3
Obuasi
Kwabre East
Ahafo Ano North
9 | Western North | Sefwi Wiawso | UDG-3
10 | Eastern | Birim Central | UDG-3
|  | New Juaben South | UDG-3
|  | Lower Manya Krobo | UDG-3
|  | Abuakwa South | UDG-3
|  | West Akim | UDG-3
11 | Volta | Ho | UDG-3
|  | Hohoe | UDG-3
12 | Central | Agona West | UDG-3
|  | Mfantseman | UDG-3
|  | Awutu Senya East | UDG-3
|  | Assin Fosu | UDG-3
13 | Western | Effia-Kwesimintsim | UDG-3
|  | Ahanta West | UDG-3
14 | Oti | Krachi East | UDG-3
15 | Ahafo | Asunafo North | UDG-3